## Hoja1
Supp | PI | Product | Qty (Pcs) | Destination | Loaded? | Follow Up W17 | RAF | Inspection Day
YUY | FH2402093 | H Mod Multi Marula 3D Bvt | 9000 | BRAZIL |  | Waiting for shipping instruction | 2025-04-18 | 2025-04-18
YUY | FH2402092 | H Mod Multi Gold 3D Bvt | 9000 | BRAZIL | Yes | Shipped | 2025-04-21 | 2025-04-10
MIL | MILES24070804 | H Mod Babosa Brush 3D Bvt | 12000 | BRAZIL | Yes | shipped | 2025-04-21 | TBA
MIL | MILES-SP25021401 | H Thick Head Rot Brush BK | 1008 | BRAZIL | Yes | Shipped | 2025-04-21 | 2025-04-17
MIL | MILES24100902 | H Mod Eleganza Plus Bvt | 14064 | BRAZIL |  | booking shipment now | 2025-04-23 | 2025-04-23
EXT | PI2411144 | H Eolic Travel Ion Bvt | 4500 | BRAZIL |  | Waiting for inspection | 2025-04-28 | 2025-04-28
RUN | RUNWE2025F16 | M SH 987 Sport Bat | 1002 | BRAZIL |  | VPE- Waiting VPE confirm PP | 2025-05-15 | TBA
TIA | ATL2024006 | H Spa Dryer Large 110 | 2004 | BRAZIL |  | Preparing production now | 2025-05-29 | TBA
TIA | ATL2024007 | H Spa Dryer Large 220 | 3000 | BRAZIL |  | Preparing production now | 2025-05-29 | TBA
HOF | 2402043A | M GCX 623 Sport Bat | 6000 | BRAZIL |  | deposit delay on Mar 26th, the RAF is on May 30th | 2025-05-30 | TBA
HOF | 2502044A | M Titanium T827 Bat | 6000 | BRAZIL |  | deposit delay on Mar 26th, the RAF is on May 30th | 2025-05-30 | TBA
UGA | UG20241012 | C T New 25 MM Bvt | 8004 | BRAZIL |  | will produce it after 60 days of production of order UG20241011 | 2025-05-31 | TBA
EXT | PI2502172 | H Eolic Travel Ion Bvt | 6000 | BRAZIL |  | VPE- Waiting VPE confirm PP | 2025-06-10 | TBA
BAN | BS-MS-V250323 | M GT GBLADE W&D USB | 2004 | BRAZIL |  | Preparing production now. | 2025-06-12 | TBA
MIL | MILES25021711 | H Mod Rot Marula Bvt | 3204 | BRAZIL |  | Preparing production now | 2025-06-15 | TBA
MIL | MILES25021709 | H Mod Rot Eleganza Plus Bvt | 15300 | BRAZIL |  | Preparing production now | 2025-06-20 | TBA
HOF | 2502032C | M Blade DLC St | 100 | BRAZIL |  | production | 2025-06-20 | TBA
HOF | 2502032C | M Blade DLC F Wedge | 100 | BRAZIL |  | production | 2025-06-20 | TBA
HOF | 2502032C | M Blade DLC Wedge | 100 | BRAZIL |  | production | 2025-06-20 | TBA
HOF | 2502032C | M Blade DLC Balding | 100 | BRAZIL |  | production | 2025-06-20 | TBA
HOF | 2502032C | M Blade DLC T-Blade | 100 | BRAZIL |  | production | 2025-06-20 | TBA
HOF | 2503052A | M GCX 630 W&D USB | 1002 | BRAZIL |  | production | 2025-06-20 | TBA
HOF | 2503067A | M Titanium T923 Bat | 4002 | BRAZIL |  | production | 2025-06-20 | TBA
HOF | 2503066A | M GCX 623 Sport Bat | 6000 | BRAZIL |  | production | 2025-06-20 | TBA
HOF | 2411201A | M Titanium T923 Bat | 15000 | BRAZIL |  | production | 2025-06-30 | TBA
RUN | RUNWE2025F08 | M SH 987 Sport Bat | 2004 | BRAZIL |  | Under production. PP was confirmed. Deposit was paid | 2025-06-30 | TBA
HOF | 2410175A | M Titanium T923 Bat | 15000 | BRAZIL |  | goods already finished inspection and now waiting for GAMA instruction to ship bcz GAMA requested to postpone its RAF to Jun30th before. | 2025-06-30 | 2025-03-17
SHG | SHG20240617-5 | M SH 700 Sport USB | 4500 | BRAZIL |  | Waiting for production | 2025-06-30 | TBA
YUY | FH2402089 | B Gold ion HotBrush Mini Bvt | 3000 | BRAZIL |  | Under production. PP was confirmed | 2025-07-01 | TBA
SHG | SHG20250324-3 | M GM Master 110 | 5004 | BRAZIL |  | waiting for PP confirmation | 2025-07-07 | TBA
MIL | MILES24111403 | H Mod Stylish Keration Brush 3D Bvt | 7002 | BRAZIL |  | Preparing production now | 2025-07-10 | TBA
MIL | MILES24100903 | H Mod Eleganza Plus Bvt | 28002 | BRAZIL |  | Preparing production now | 2025-07-10 | TBA
SHG | SHG20250324-4 | M GM Master 220 | 5004 | BRAZIL |  | waiting for PP confirmation | 2025-07-10 | TBA
MIL | MILES25021707 | H Mod Eleganza Plus Bvt | 42192 | BRAZIL |  | Preparing production now | 2025-07-16 | TBA
MIL | MILES24061506 | H Mod Babosa Brush 3D Bvt | 4002 | BRAZIL |  | Preparing production now | 2025-07-30 | TBA
MIL | MILES24111404 | H Mod Babosa Brush 3D Bvt | 5004 | BRAZIL |  | Preparing production now | 2025-07-30 | TBA
MIL | MILES24111405 | H Mod Lichia Brush 3D Bvt | 2004 | BRAZIL |  | Preparing production now | 2025-07-30 | TBA
MIL | MILES25021708 | H Mod Eleganza Plus Bvt | 28128 | BRAZIL |  | Preparing production now | 2025-07-31 | TBA
ANI | ATG2523A009 | M SE GBS Abs Shaver Bvt | 2004 | BRAZIL |  | Under production. PP was confirmed. Deposit was paid | 2025-08-10 | TBA
MIL | MILES24061504 | H Mod Stylish Keration Brush 3D Bvt | 10002 | BRAZIL |  | Preparing production now | 2025-08-10 | TBA
UGA | UG20250212 | C T New 25 MM Bvt | 10002 | BRAZIL |  | will produce order UG20250212 by the end of July or mid-August | 2025-08-15 | TBA
MIL | MILES25021710 | H Mod Rot Eleganza Plus Bvt | 10002 | BRAZIL |  | Preparing production now | 2025-08-15 | TBA
MIL | MILES25021712 | H Mod Rot Marula Bvt | 3204 | BRAZIL |  | Preparing production now | 2025-08-15 | TBA
MIL | MILES25032402 | H Mod Babosa Brush 3D Bvt | 14064 | BRAZIL |  | Preparing production now | 2025-08-24 | TBA
MIL | MILES25032403 | H Mod Eleganza Plus Bvt | 10002 | BRAZIL |  | Preparing production now | 2025-08-24 | TBA
SHE | Y241124 | C GP Salon 9mm Silk Bvt | 1002 | BRAZIL |  | GAMA requested postponed RAF to Aug. 30. on Feb. 18 | 2025-08-30 | TBA
SHE | Y241125 | C GP Salon 25mm Silk Bvt | 1002 | BRAZIL |  | GAMA requested postponed RAF to Aug. 30. on Feb. 18 | 2025-08-30 | TBA
SHE | Y241126 | C GP Salon 32mm Silk Bvt | 1002 | BRAZIL |  | GAMA requested postponed RAF to Aug. 30. on Feb. 18 | 2025-08-30 | TBA
SHE | Y241127 | C GP Salon 38mm Silk Bvt | 1002 | BRAZIL |  | GAMA requested postponed RAF to Aug. 30. on Feb. 18 | 2025-08-30 | TBA
YUY | FH2402090 | B Gold ion HotBrush Mini Bvt | 3000 | BRAZIL |  | Under production. PP was confirmed | 2025-09-01 | TBA
EXT | PI2502173 | H Eolic Travel Ion Bvt | 6000 | BRAZIL |  | VPE- Waiting VPE confirm PP | 2025-09-10 | TBA
MIL | MILES24061503 | H Mod Stylish Keration Brush 3D Bvt | 14004 | BRAZIL |  | Preparing production now | 2025-09-10 | TBA
HOF | 2503048C | M GT 557 Sport WD Bat | 3000 | BRAZIL |  | production | 2025-09-20 | TBA
MIL | MILES25032404 | H Mod Eleganza Plus Bvt | 14064 | BRAZIL |  | Preparing production now | 2025-09-28 | TBA
TIA | ATL2025001 | H Spa Dryer Large 220 | 2004 | BRAZIL |  | Preparing production now | 2025-09-28 | TBA
FAD | TY20220940REV | I GP IHT Gevo W&L D OA UH Bvt | 3000 | BRAZIL |  | postpone the RAF according GAMA request.same power and quality problems with TY20230500,our team had sent samples to PCBA supplier to change the product program | TBA | Nt available
SAI | SDM24035GA281 | C GP Bravo Bubbles Silk Led Bvt | 600 | BRAZIL |  | VPE-Waiting VPE confirm PP. Deposit was paid | TBA | TBA
SAI | SDM24028GA274 | C GP Bravo 9mm Silk Led Bvt | 600 | BRAZIL |  | VPE-Waiting VPE confirm PP. Deposit was paid | TBA | TBA
SAI | SDM24032GA278 | C GP Bravo 40mm Silk Led Bvt | 800 | BRAZIL |  | VPE-Waiting VPE confirm PP. Deposit was paid | TBA | TBA
SAI | SDM24029GA275 | C GP Bravo 19mm Silk Led Bvt | 1002 | BRAZIL |  | VPE-Waiting VPE confirm PP. Deposit was paid | TBA | TBA
SAI | SDM24034GA280 | C GP Bravo Triferro Silk Led Bvt | 1002 | BRAZIL |  | VPE-Waiting VPE confirm PP. Deposit was paid | TBA | TBA
SAI | SDM24033GA279 | C GP Bravo Conic Silk Led Bvt | 600 | BRAZIL |  | VPE-Waiting VPE confirm PP. Deposit was paid | TBA | TBA
SAI | SDM24031GA277 | C GP Bravo 32mm Silk Led Bvt | 1002 | BRAZIL |  | VPE-Waiting VPE confirm PP. Deposit was paid | TBA | TBA
SAI | SDM24030GA276 | C GP Bravo 25mm Silk Led Bvt | 1002 | BRAZIL |  | VPE-Waiting VPE confirm PP. Deposit was paid | TBA | TBA
SAN | G2409L235 | I IHT GP IQ Led OA RG Bvt | 360 | BRAZIL |  | After all pending issues solved as described in the emails for Bravo and IQ, then Sanye will start production. | TBA | TBA
SAN | G2409L231 | I IHT GP Bravo Led OA Bvt | 1002 | BRAZIL |  | After all pending issues solved as described in the emails for Bravo and IQ, then Sanye will start production. | TBA | TBA
SAN | G2409L234 | I IHT GP IQ Led OA RD Bvt | 360 | BRAZIL |  | After all pending issues solved as described in the emails for Bravo and IQ, then Sanye will start production. | TBA | TBA
SAN | G2409L233 | I IHT GP IQ Led OA BL Bvt | 360 | BRAZIL |  | After all pending issues solved as described in the emails for Bravo and IQ, then Sanye will start production. | TBA | TBA
SAN | G2409L232 | I IHT GP IQ Led OA BK Bvt | 360 | BRAZIL |  | After all pending issues solved as described in the emails for Bravo and IQ, then Sanye will start production. | TBA | TBA
YUY | FH2502033 | H Mod Multi Marula 3D Bvt | 3204 | BRAZIL |  | Supplier-waiting supplier provide PP | TBA | TBA
UGA | UG20250302 | C T New 19 MM Bvt | 1500 | BRAZIL |  | will send you PP soon | TBA | TBA
UGA | UG20250303 | C T New 33 MM Bvt | 1500 | BRAZIL |  | will send you PP soon | TBA | TBA
MIL | ML18122401 | H GP IQ Lite MAX Red 110 | 1002 | BRAZIL |  | Preparing production now | 2025-07-20 | TBA
MIL | ML18122403 | H GP IQ Lite MAX BK 110 | 1002 | BRAZIL |  | Preparing production now | 2025-07-20 | TBA
MIL | ML18122405 | H GP IQ Lite MAX GR 110 | 1002 | BRAZIL |  | Preparing production now | 2025-07-20 | TBA
MIL | ML18122407 | H GP IQ Lite MAX BL 110 | 1002 | BRAZIL |  | Preparing production now | 2025-07-20 | TBA
MIL | ML17121903 | H GP IQ Lite Red 110 | 1002 | BRAZIL |  | Preparing production now | 2025-09-30 | TBA
MIL | ML17121904 | H GP IQ Lite Red 220 | 1002 | BRAZIL |  | Preparing production now | 2025-09-30 | TBA